## Summary
datacore.com.sa — improvement register
141 items. Filter the Improvements sheet by Impact to plan a phase.
Basis: 'Seen' = observed in your screen recording · 'Measured' = calculated · 'Verify' = needs checking against the live code · 'Planning' = new work.
Area | High | Med | Low | Total
Accessibility | 6 | 11 | 1 | 18
Typography | 1 | 6 | 3 | 10
Layout | 3 | 8 | 4 | 15
Navigation | 3 | 4 | 3 | 10
Conversion | 6 | 7 | 1 | 14
Content | 5 | 8 | 1 | 14
Services | 1 | 4 | 1 | 6
Projects | 3 | 3 | 1 | 7
Contact | 1 | 6 | 1 | 8
Performance | 5 | 6 | 0 | 11
SEO | 5 | 5 | 1 | 11
Localisation | 3 | 3 | 1 | 7
Legal | 2 | 3 | 0 | 5
Analytics | 3 | 2 | 0 | 5
Total | 47 | 76 | 18 | 141
Suggested phasing
Phase 1 — week 1 | Every High-impact / Small-effort item. Contrast fix, chat widget, hero rewrite, the three layout bugs, tel: links, WhatsApp.
Phase 2 — weeks 2–5 | Typography unification, service page content rewrite, projects template and filters, performance pass, SEO foundations.
Phase 3 — weeks 4–10 | Products catalogue and RFQ module, admin panel, Excel import.
Phase 4 — after launch | Arabic site, location landing pages, project photography.

## Improvements
# | Area | Where | What's wrong | What to do | Impact | Effort | Basis | Owner | Done
1 | Accessibility | Site-wide | Brand teal #13BEA0 on white measures 2.36:1. WCAG AA needs 4.5:1 for text, 3:1 for controls. | Introduce #07806B as the interactive teal for all text and button fills. Keep #13BEA0 for logo, icons and decorative fills only. | High | S | Measured
2 | Accessibility | Hero, all pages | White 'GET IN TOUCH' label on the teal button is 2.36:1 — unreadable in daylight on a phone. | Either darken the fill to #07806B and keep white text (4.87:1), or keep the bright teal and set the label to #18191E (7.44:1). | High | S | Measured
3 | Accessibility | Main nav | Active page is signalled by teal colour alone, and that teal fails contrast. | Add a weight change or solid underline so the active state does not depend on colour. | High | S | Seen
4 | Accessibility | Site-wide | No visible keyboard focus indicator observed. | Add a :focus-visible outline of 2px in #07806B with 2px offset on every interactive element. | High | S | Verify
5 | Accessibility | Services mega-menu | Menu appears to open on hover only, which excludes keyboard and touch users. | Open on click and Enter, close on Escape, and manage focus into the panel. | High | M | Verify
6 | Accessibility | Home hero | Headline sits directly on a photograph with no scrim, so contrast depends on which image loads. | Add a gradient overlay behind the text block so contrast holds for any hero image. | High | S | Seen
7 | Accessibility | Home hero | Carousel auto-rotates with no pause control (WCAG 2.2.2). | Remove the carousel, or add a visible pause and honour prefers-reduced-motion. | Med | S | Seen
8 | Accessibility | Section headings | Giant ghosted watermark words are real text, so screen readers announce 'SERVICE SERVICE'. | Mark them aria-hidden, or render as a background image. | Med | S | Seen
9 | Accessibility | Site-wide | No skip-to-content link. | Add a visually hidden skip link as the first focusable element. | Med | S | Verify
10 | Accessibility | Forms | Fields may rely on placeholder text instead of persistent labels. | Give every field a visible label that stays after the user types. | Med | S | Verify
11 | Accessibility | Carousel controls | Prev/next arrows are small, unlabelled and likely under the 44px minimum target. | Add aria-labels and enlarge hit areas to 44x44px. | Med | S | Seen
12 | Accessibility | Logo marquee | Continuously auto-scrolling logo strip with no pause. | Pause on hover and on focus, and stop entirely under prefers-reduced-motion. | Med | S | Seen
13 | Accessibility | Site-wide | Images may be missing alt text. | Audit every image. Descriptive alt for content images, empty alt for decorative ones. | Med | M | Verify
14 | Accessibility | Site-wide | Layout may break at 200% browser zoom, which fixed-height hero sections usually do. | Test at 200% and 400%; convert fixed heights to min-height. | Med | M | Verify
15 | Accessibility | Chat widget | Widget opens itself and may not be dismissible by keyboard. | Ensure Escape closes it and focus returns to the page. | Med | S | Seen
16 | Accessibility | Contact page | Grey label text ('VISIT US AT SAUDI ARABIA') looks close to the 4.5:1 threshold. | Measure and darken to at least #5A6169. | Med | S | Verify
17 | Accessibility | Footer | Small light text on near-black background across the whole footer. | Raise footer body text to 15px and check every colour pair against AA. | Med | S | Seen
18 | Accessibility | Site-wide | Heading levels may skip (h1 to h3) because headings are styled by size. | Audit the heading outline of every template; style by class, not by tag choice. | Low | M | Verify
19 | Typography | Site-wide | Two different type systems: a serif on home and about, a geometric sans on service pages. Visitors landing from search see a different company. | Pick one system. Keep the serif for home and about as the brand voice, standardise everything below on the sans. | High | M | Seen
20 | Typography | Main nav | All-caps with wide letterspacing across six items slows scanning. | Move to sentence case, or cut tracking to roughly 0.02em. | Med | S | Seen
21 | Typography | Home headings | Headline split across two weights ('BRINGING YOUR' light / 'VISION TO LIFE' bold) with no semantic reason for the break. | Set the whole headline in one weight, or split on a meaningful clause. | Med | S | Seen
22 | Typography | Site-wide | No consistent type scale — heading sizes jump unpredictably between sections. | Define a modular scale and apply it as tokens. | Med | M | Seen
23 | Typography | Service pages | Body line length runs past 90 characters on wide screens. | Cap body measure at 70–75 characters. | Med | S | Seen
24 | Typography | Site-wide | Wide display letterspacing appears to be applied at smaller sizes too, where it hurts legibility. | Scale tracking inversely with size: loose for display, near zero for body. | Low | S | Seen
25 | Typography | Site-wide | Web font loading strategy unknown; invisible text during load is likely. | Set font-display: swap and preload the two most-used weights. | Med | S | Verify
26 | Typography | Site-wide | Probably loading more font weights than are used. | Subset to the weights actually in the design; drop the rest. | Low | S | Verify
27 | Typography | Stats, phone numbers | Proportional figures make numbers ragged in columns. | Enable tabular figures (font-variant-numeric) for stats, prices and phone numbers. | Low | S | Seen
28 | Typography | Future Arabic build | Latin typeface has no matching Arabic companion. | Choose a family with a real Arabic cut — IBM Plex Sans Arabic, Cairo or Noto Kufi Arabic. | Med | M | Planning
29 | Layout | Home — Proven Expertise | Roughly half a viewport of empty space inside a bordered box before the stats appear. | Remove the dead space and bring the stats up next to the heading. | High | S | Seen
30 | Layout | Access control page | Sticky header overlaps the hero and clips the 'Request a consultation' button in half. | Fix the z-index and add scroll-padding-top equal to the header height. | High | S | Seen
31 | Layout | Contact page | Google map bleeds to the far left viewport edge while every other element is inset ~92px. | Bring the map inside the container, or make the full-bleed treatment deliberate and symmetrical. | High | S | Seen
32 | Layout | Site-wide | Content max-width and side gutters vary between sections. | Define one container width and one gutter scale; apply everywhere. | Med | M | Seen
33 | Layout | Site-wide | Section padding is inconsistent, so vertical rhythm is uneven when scrolling. | Standardise on a spacing scale of three or four section-padding values. | Med | M | Seen
34 | Layout | Home | Ghosted watermark words are cropped by the viewport edge, reading as a rendering fault. | Contain them within the grid, or remove the device. | Med | S | Seen
35 | Layout | Home | Brand logos appear twice — 'Brands That Trust Us' and 'Trusted Alliances' — with overlap between them. | Merge into a single logo wall, sorted, with equal optical sizing. | Med | S | Seen
36 | Layout | Home — Expertise | A border box wraps a section for no structural reason. | Remove the border or give it a purpose. | Low | S | Seen
37 | Layout | Home — services grid | Two-up card grid leaves large empty margins on desktop. | Move to three-up above 1200px. | Med | S | Seen
38 | Layout | Home — success stories | Cards end at unequal heights. | Equalise card heights and truncate excerpts to a fixed line count. | Low | S | Seen
39 | Layout | Blog cards | Thumbnail aspect ratios vary between cards. | Fix one aspect ratio and use object-fit: cover. | Low | S | Seen
40 | Layout | Site-wide | Three competing calls to action stack in the bottom-right: chat bubble, floating side tab, and the CTA band. | Keep one. The chat bubble is the natural survivor. | Med | S | Seen
41 | Layout | Service & project pages | No breadcrumbs, so deep pages have no sense of place. | Add breadcrumbs to all pages below the top level. | Med | S | Seen
42 | Layout | Mobile | Mega-menu behaviour on mobile is unverified; a flat list of ten items becomes a long scroll. | Collapse into grouped accordions on mobile. | Med | M | Verify
43 | Layout | Footer | Dense, dark, with five columns of small links. | Increase spacing and text size; group by user intent. | Low | S | Seen
44 | Navigation | Services menu | Around ten services sit in one flat list. | Group into disciplines: ICT & Networks, Security, Audio Visual, Datacentre, Life Safety. | Med | M | Seen
45 | Navigation | Site-wide | No site search anywhere. | Add search — essential once a 1000-SKU catalogue exists. | High | M | Seen
46 | Navigation | Main nav | Products is missing. | Add Products as a top-level item beside Services. | High | S | Planning
47 | Navigation | Footer / nav | Blog is called 'Technology Insights' in one place and 'Blog' in another. | Pick one name and use it everywhere. | Low | S | Seen
48 | Navigation | Careers | Careers appears only in the footer, despite an active careers email. | Promote to the About menu with real vacancies. | Med | M | Seen
49 | Navigation | Language switcher | An ENGLISH dropdown with a chevron implies other languages that do not exist. | Ship Arabic, or remove the chevron until it does. | Med | S | Seen
50 | Navigation | Site-wide | No sitemap page for humans. | Add one; it also helps crawlers reach deep project pages. | Low | S | Verify
51 | Navigation | Error handling | Unknown whether a branded 404 exists. | Build a 404 that offers search, services and contact. | Low | S | Verify
52 | Navigation | Service pages | No links between related services. | Add a related-services strip to each service page. | Med | S | Seen
53 | Navigation | Site-wide | Projects, services and (soon) products are not cross-linked. | Link each project to the services delivered and the equipment used. | High | M | Planning
54 | Conversion | Home hero | Two-slide carousel — the second slide is seen by almost nobody. | Replace with a single fixed hero carrying your strongest message. | High | S | Seen
55 | Conversion | Home hero | Copy says 'We start wherever you are and work with you to understand your needs' — true of any business. | Rewrite to name the disciplines, the market and the track record. | High | S | Seen
56 | Conversion | Home hero | 'GET IN TOUCH' does not say what happens next. | Use 'Request a consultation' or 'Get a quote'. | Med | S | Seen
57 | Conversion | Home hero | Only one call to action, aimed at people already ready to talk. | Add a secondary low-commitment CTA: 'See our projects'. | Med | S | Seen
58 | Conversion | Site-wide | Chat widget auto-opens on load and covers the hero CTA on every page. | Start collapsed; open only after scroll or on click. | High | S | Seen
59 | Conversion | Home | Stats (1000+, 100+, 03, 15+) sit far down the page. | Move them into or directly below the hero. | Med | S | Seen
60 | Conversion | Home stats | '03' is meaningless without a label. | Label every figure — '3 countries', '15+ years'. | Med | S | Seen
61 | Conversion | Home | Nothing tells a first-time visitor what you do until several screens down. | Add a five-discipline strip immediately below the hero. | High | S | Seen
62 | Conversion | Home | No named case study with a measurable result. | Feature one project with a client, a scope and an outcome. | High | M | Seen
63 | Conversion | Site-wide | The identical 'Speak with an expert' band appears on every page — one generic funnel. | Vary the offer by context: request a site survey on service pages, request a quote on products. | High | M | Seen
64 | Conversion | Site-wide | 'Download brochure' is untracked and ungated. | Track it as a conversion; consider a light email gate. | Med | S | Seen
65 | Conversion | Site-wide | No lead magnet with genuine professional value. | Publish an ELV design checklist or a Cat6A vs fibre selection guide. | Med | M | Planning
66 | Conversion | Above the fold | No trust signals visible before scrolling. | Add years in business, partner tiers and certifications to the hero area. | Med | S | Seen
67 | Conversion | Home | Client logo wall runs as an auto-scrolling marquee, so no logo is on screen long. | Make it a static grid. | Low | S | Seen
68 | Content | All service pages | Copy is interchangeable: 'secure and scalable systems that adapt to your business requirements'. | Rewrite each page around what is technically distinct about that discipline. | High | L | Seen
69 | Content | Service pages | No standards referenced anywhere. | Name EN 54-16 and EN 54-24 on PA and voice alarm, SASO, Saudi Building Code, ISO 27001. | High | M | Seen
70 | Content | Service pages | Manufacturer relationships are shown as logos with no context. | State the partner tier and what it authorises you to do. | High | S | Seen
71 | Content | Service pages | No description of scope boundaries. | Spell out design, supply, installation, commissioning, training and SLA. | High | M | Seen
72 | Content | Service pages | No indication of project size you handle. | Give typical ranges — device counts, floor areas, timelines. | Med | M | Seen
73 | Content | Service pages | No FAQs. | Add five to eight real procurement questions per service. | Med | M | Seen
74 | Content | About | No named people anywhere on the site. | Add a leadership section with names, roles and photographs. | Med | M | Seen
75 | Content | About | 'How we get started' reads as generic process language. | Describe your actual stages, with what the client receives at each. | Med | M | Seen
76 | Content | Blog | Posts are general explainers ('What is a public address system?'). | Write from delivered projects — the technical decisions and why. | Med | L | Seen
77 | Content | Blog | No visible author or date. | Add both; undated technical content ages badly and Google discounts it. | Low | S | Seen
78 | Content | Site-wide | No downloadable line card of brands carried. | Publish one as a PDF — consultants ask for it constantly. | Med | S | Planning
79 | Content | Site-wide | No Vision 2030 or localisation framing for government-facing work. | Add a short section on local content and Vision 2030 alignment. | Med | M | Planning
80 | Content | Site-wide | Company profile PDF not offered. | Publish a current company profile for tender submissions. | Med | S | Planning
81 | Content | Home | Nothing distinguishes you from any other integrator in Riyadh. | Decide the one claim you own and lead with it everywhere. | High | M | Seen
82 | Services | All service pages | Hero imagery is generic stock. | Use photographs from your own installations. | Med | M | Seen
83 | Services | All service pages | No link to relevant products. | Add a related-products strip once the catalogue is live. | High | M | Planning
84 | Services | All service pages | No capability or specification table. | Add a table of systems, scale and standards covered. | Med | M | Seen
85 | Services | All service pages | No project examples on the page. | Show two or three relevant projects per service. | Med | M | Seen
86 | Services | All service pages | Enquiry goes to the same generic form. | Pre-fill the form with the service name so sales knows the context. | Med | S | Seen
87 | Services | Long service pages | No in-page navigation. | Add a sticky anchor nav for sub-sections. | Low | S | Seen
88 | Projects | Projects page | Filter is a single 'All Services' dropdown. | Add filters for sector, service, country and year. | High | M | Seen
89 | Projects | Project detail | No consistent template across case studies. | Standardise: client, sector, scope, systems, equipment, duration, outcome. | High | M | Seen
90 | Projects | Project detail | No equipment list. | List the systems deployed and link each to the catalogue. | High | M | Planning
91 | Projects | Project detail | No client quotes. | Get a short testimonial on every project where the client permits it. | Med | M | Seen
92 | Projects | Projects page | Photography is inconsistent in framing and colour. | Set a shooting standard and reshoot the flagship projects. | Med | L | Seen
93 | Projects | Projects page | No sense of volume by sector. | Show counts by sector — banking, healthcare, education, government. | Med | S | Seen
94 | Projects | Projects page | No case study is downloadable. | Offer a one-page PDF per project for tender packs. | Low | M | Planning
95 | Contact | Contact page | One form for all enquiry types. | Split into sales, careers and support, each routed to the right inbox. | Med | M | Seen
96 | Contact | Contact page | No WhatsApp contact, which is the default business channel in the Kingdom. | Add a WhatsApp Business link alongside the phone numbers. | High | S | Seen
97 | Contact | Contact page | No office hours or holiday notice. | Publish hours and note Eid and national holiday closures. | Med | S | Seen
98 | Contact | Contact page | Phone numbers are plain text. | Make them tel: links so mobile users can tap to call. | Med | S | Seen
99 | Contact | Contact form | No reference number on submission. | Return a reference number and send an acknowledgement email. | Med | M | Seen
100 | Contact | Contact form | Spam protection unknown. | Use a honeypot and rate limiting rather than a visible captcha. | Med | S | Verify
101 | Contact | Contact page | Google Business Profiles not linked. | Link both profiles and keep hours in sync. | Low | S | Verify
102 | Contact | Contact page | Map is a heavy embed loaded immediately. | Load a static image and swap to the interactive map on click. | Med | S | Seen
103 | Performance | Site-wide | Large full-bleed photographs at roughly 1900px, format unknown. | Serve AVIF with WebP fallback and a responsive srcset. | High | M | Verify
104 | Performance | Site-wide | Below-fold images likely load eagerly. | Add loading=lazy everywhere except the hero. | High | S | Verify
105 | Performance | Home hero | Hero image is the LCP element and is probably not preloaded. | Preload it and mark it fetchpriority=high. | High | S | Verify
106 | Performance | Site-wide | Third-party chat script loads on every page at first paint. | Defer until scroll or interaction. | High | S | Seen
107 | Performance | Site-wide | Images may lack explicit dimensions, causing layout shift. | Set width and height on every image. | Med | S | Verify
108 | Performance | Site-wide | Continuously animating logo marquee costs main-thread time on every page. | Use a static grid, or animate with transform only. | Med | S | Seen
109 | Performance | Server | Compression and cache headers unverified. | Enable Brotli and set long cache lifetimes on static assets. | Med | S | Verify
110 | Performance | Server | Origin location unknown for a Gulf audience. | Use a CDN with a Middle East point of presence. | Med | M | Verify
111 | Performance | Site-wide | No performance budget in place. | Target LCP under 2.5s and CLS under 0.1 on 4G. | Med | M | Planning
112 | Performance | Site-wide | Third-party script inventory unknown. | Audit every tag; remove anything unused. | Med | S | Verify
113 | Performance | Products module | 1000+ SKUs will make naive queries slow. | Index the filter columns and paginate server-side from day one. | High | M | Planning
114 | SEO | Site-wide | Title tags and meta descriptions unverified and likely templated. | Write unique ones for every page, with the city where relevant. | High | M | Verify
115 | SEO | Site-wide | No structured data observed. | Add Organization and LocalBusiness schema for all three offices. | High | M | Verify
116 | SEO | Service pages | No Service schema. | Add Service schema with areaServed. | Med | S | Planning
117 | SEO | Service pages | No location-specific landing pages. | Build pages for Riyadh, Jeddah, Dammam and Dubai per major service. | High | L | Planning
118 | SEO | Site-wide | Content targets category terms rather than buying terms. | Target commercial intent: 'access control system installation Riyadh'. | High | M | Planning
119 | SEO | Site-wide | Sitemap and robots.txt unverified. | Publish an XML sitemap and check robots.txt is not blocking assets. | Med | S | Verify
120 | SEO | Site-wide | Canonical tags unverified. | Add self-referencing canonicals; critical once filtered product URLs exist. | Med | S | Verify
121 | SEO | Site-wide | Open Graph and Twitter card tags unverified. | Add them so shared links render properly on LinkedIn and WhatsApp. | Med | S | Verify
122 | SEO | Blog | No FAQ or Article schema. | Add Article schema to posts and FAQPage where FAQs are added. | Low | S | Planning
123 | SEO | Products module | Catalogue pages need their own SEO treatment. | Add Product schema, unique titles per SKU, and noindex on filtered permutations. | High | M | Planning
124 | SEO | Site-wide | Search Console coverage unknown. | Verify the property and monitor coverage and Core Web Vitals. | Med | S | Verify
125 | Localisation | Site-wide | No Arabic version despite a Riyadh headquarters and government-facing work. | Build a full Arabic site, not a translated widget. | High | L | Seen
126 | Localisation | Site-wide | Layout uses physical CSS properties, so RTL will require a stylesheet rewrite. | Convert to logical properties now, before the Arabic build. | High | M | Planning
127 | Localisation | Site-wide | No hreflang. | Add hreflang pairs for ar-SA and en-SA. | Med | S | Planning
128 | Localisation | Site-wide | Arabic needs different line-height and size to read comfortably at the same optical scale. | Set separate typographic tokens for the Arabic build. | Med | M | Planning
129 | Localisation | Site-wide | Machine translation will read badly to a Saudi procurement audience. | Have the Arabic transcreated by someone who knows the sector vocabulary. | High | L | Planning
130 | Localisation | Site-wide | Logo mark must not be mirrored when the layout flips. | Lock the mark; mirror only the layout. | Low | S | Planning
131 | Localisation | Products module | Product names need Arabic from the first import, not retrofitted. | Arabic name and description columns are already in the import template. | Med | S | Planning
132 | Legal | Footer | Commercial Registration and VAT numbers are not displayed. | Publish CR and VAT numbers in the footer as required for a Saudi commercial site. | High | S | Seen
133 | Legal | Privacy policy | Policy predates PDPL in all likelihood. | Update for Saudi PDPL: lawful basis, retention, data subject rights, contact. | High | M | Verify
134 | Legal | Site-wide | No cookie consent observed. | Add consent covering analytics and the chat widget. | Med | M | Verify
135 | Legal | Site-wide | Certifications not displayed. | Show ISO certificates and manufacturer accreditations with expiry dates. | Med | S | Seen
136 | Legal | Products module | RFQ collects personal and company data. | Add a purpose statement and retention policy to the RFQ form. | Med | S | Planning
137 | Analytics | Site-wide | Conversion tracking unverified. | Set up GA4 with events on every CTA, form submission and brochure download. | High | M | Verify
138 | Analytics | Site-wide | No qualitative data on where visitors stall. | Add a heatmap and session recording tool for one month. | Med | S | Planning
139 | Analytics | Forms | Abandonment is invisible. | Track field-level abandonment on the contact and RFQ forms. | Med | M | Planning
140 | Analytics | Products module | No way to know which SKUs generate demand. | Log catalogue searches with no results — that is your stocking gap list. | High | S | Planning
141 | Analytics | Site-wide | No baseline before the redesign. | Capture four weeks of baseline metrics before shipping changes. | High | S | Planning