## Register
# | Area | Severity | Problem — V2.0 baseline | Status | Resolution / notes
1 | Build & tooling | Critical | build.py fails with SyntaxError on Python 3.9-3.11 (backslash inside an f-string expression) although README promises Python 3.9+; the build did not run at all on this machine's Python 3.11. | Fixed — V2.1 | Navigation link builder rewritten without the 3.12-only construct; build verified on 3.11 and 3.13.
2 | Build & tooling | High | check.py wrote its temp JS file to a hardcoded /tmp path — FileNotFoundError on Windows, so the verifier crashed instead of verifying. | Fixed — V2.1 | tempfile.mkstemp used; portable on Windows and POSIX.
3 | Build & tooling | High | check.py wrote the temp file without UTF-8 encoding — UnicodeEncodeError on the catalogue's Arabic strings under Windows cp1252. | Fixed — V2.1 | Temp file written with encoding='utf-8'.
4 | Build & tooling | Medium | check.py crashed with FileNotFoundError when node is not installed, instead of skipping the JS syntax check. | Fixed — V2.1 | shutil.which('node'); check skipped with a visible warning when absent.
5 | Build & tooling | Medium | Check marks (u2713/u2717) in script output crash under cp1252 consoles and pipes on Windows. | Fixed — V2.3 | sys.stdout reconfigured to UTF-8 in check.py and manage.py.
6 | Build & tooling | Low | check.py's HTML parser listed option and iframe as void elements — nesting errors involving them were invisible. | Fixed — V2.1 | Removed from the VOID set; both are properly closed in the templates.
7 | Build & tooling | Low | check.py demanded exactly 14 pages, so any legitimately added page would fail the build check. | Fixed — V2.1 | Changed to a minimum-of-14 floor; 20 pages now verified.
8 | Build & tooling | Medium | No build-time guard that the EN and AR content structures stay parallel — drift would ship silently. | Fixed — V2.2 | Assertions compare discipline list shapes across languages at build time.
9 | Build & tooling | Medium | Service blurbs looked up with .get(name, '') — a missing or misspelled key shipped an empty card with no error. | Fixed — V2.2 | Direct indexing plus a build-time assertion that every service has a blurb in both languages.
10 | Build & tooling | High | No validation of catalogue data existed anywhere: duplicate SKUs, unknown icons, missing lead times or fields could all ship. | Fixed — V2.3 | manage.py check validates all of it (and build auto-runs after every manage.py change).
11 | Dead & wrong links | Critical | 'Company profile (PDF)' button in the CTA band on every page linked /assets1/images/DC COMPANY PROFILE.pdf — an old-site path that 404s from this build. | Fixed — V2.2 | Button removed with a TODO to restore when the client supplies the PDF (it is on the needed-from-client list); catalogue button takes the slot.
12 | Dead & wrong links | High | Footer 'Careers' linked /career — an old-site route, 404 here. | Fixed — V2.2 | Careers points at the contact page, which has careers@ and a Careers enquiry type; a real careers template stays on the backlog.
13 | Dead & wrong links | High | Footer 'Terms of service' linked /terms-service — 404; the page does not exist in this build. | Fixed — V2.2 | Real stub page generated in both languages, noindex, clearly marked as awaiting final legal text.
14 | Dead & wrong links | High | Footer 'Privacy policy' linked /privacy-policy — 404. A privacy policy is required under PDPL for a Saudi commercial site. | Fixed — V2.2 | Stub page generated (noindex); the real text remains a launch blocker on the client list.
15 | Dead & wrong links | High | Every insight/post title linked /blog — 404. | Fixed — V2.2 | Home-page cards link to the insights listing; on the insights page titles are plain headings until the post template exists.
16 | Dead & wrong links | Critical | All 38 service cards carried two links each to /service-details/<number> — a URL scheme that both 404s and does not match the live site's slugs. | Fixed — V2.2 | Cards render unlinked until the detail template is built; the correct future slug for each of the 38 services is recorded in content.SERVICE_SLUGS.
17 | Dead & wrong links | High | Service-detail links collided: the index used was per-discipline, so every discipline's first service pointed at the same URL. | Fixed — V2.2 | Same resolution — unlinked now, slug map for later.
18 | Dead & wrong links | High | Projects page sector filter chips were href='#' decoys: clicking jumped to the top and filtered nothing, while the lede promised filtering. | Fixed — V2.2 | Chips are buttons with a real client-side sector filter and aria-pressed state.
19 | Dead & wrong links | Medium | Services 'All disciplines' chip was href='#' — jump to page top, no state change. | Fixed — V2.2 | Anchors to the list start; chips track the active selection on click.
20 | Dead & wrong links | High | No 404 page existed to catch any of the dead ends above. | Fixed — V2.2 | Branded 404 in both languages (noindex), with a route home.
21 | Contact & forms | Critical | The contact form had onsubmit='return false' — every filled enquiry was silently discarded with zero feedback. | Fixed — V2.2 | Submit now opens a pre-filled email to sales@datacore.com.sa built from the fields (native required validation first). Swap for a POST when the back end lands.
22 | Contact & forms | High | The form note promised 'we acknowledge every enquiry with a reference number' while the form sent nothing at all. | Fixed — V2.2 | The promise is now backed by a real channel (email to sales@).
23 | Contact & forms | High | The RFQ confirmation displayed a fabricated reference number (RFQ-2026-0417) as if it were real. | Fixed — V2.2 | Removed; the confirmation states the response commitment without inventing a reference.
24 | Contact & forms | High | RFQ send accepted a completely empty contact block — name, email and phone all '—', unanswerable. | Fixed — V2.2 | Send requires a name plus an email or phone; localized inline message and focus on the missing field.
25 | Contact & forms | Medium | Contact form fields had no name attributes — breaks browser autofill and future back-end wiring. | Fixed — V2.2 | name attributes on all fields.
26 | Contact & forms | Low | No autocomplete attributes (name, organization, email, tel). | Fixed — V2.2 | Added on contact form and RFQ contact fields.
27 | Contact & forms | High | RFQ drawer labels were not associated with their inputs (no for/id) — screen readers announced unnamed fields. | Fixed — V2.2 | Explicit for/id association on every RFQ field.
28 | Contact & forms | Medium | The WhatsApp link uses the Riyadh landline number — confirm it actually runs WhatsApp Business, or supply the right mobile. | Blocker — client input | Number centralized in content.py (WHATSAPP) with a TODO; one-line change when confirmed.
29 | Catalogue | High | The RFQ basket was lost on any navigation or reload. | Fixed — V2.2 | Basket persists in localStorage (guarded try/catch so private windows and file:// degrade gracefully); restored on load, unknown SKUs dropped.
30 | Catalogue | Critical | Product details could only be opened with a mouse — thumbnails and titles were divs/headings with click handlers, unreachable by keyboard. | Fixed — V2.2 | Thumbnails and titles are real buttons with accessible names; fully keyboard operable.
31 | Catalogue | High | Closed drawers stayed keyboard-tabbable while aria-hidden — focus could vanish into invisible UI. | Fixed — V2.2 | Drawers toggle visibility with the slide transition; nothing inside is reachable while closed.
32 | Catalogue | Medium | No focus management: opening a drawer left focus behind it; closing did not return focus. | Fixed — V2.2 | Focus moves to the drawer's close button on open and returns to the opener on close.
33 | Catalogue | Medium | Drawers lacked dialog semantics (role, aria-modal, accessible name). | Fixed — V2.2 | role='dialog', aria-modal='true', aria-label on both drawers.
34 | Catalogue | High | 'Download datasheet (PDF)' rendered on every product as a dead href='#' link. | Fixed — V2.2 | Removed until real datasheets exist; misleading UI is worse than absence.
35 | Catalogue | Low | Adding from the details drawer did not update that drawer's own button to 'Added'. | Fixed — V2.2 | The drawer footer re-renders in sync.
36 | Catalogue | Low | 'Send request — 1 units' — pluralization ignored the count (EN). | Fixed — V2.2 | unit/units switch; Arabic uses the correct invariant form.
37 | Catalogue | Medium | Search ignored spec values — 'PoE+', 'IP67' or 'Cat6A' found nothing despite being on the cards. | Fixed — V2.2 | Spec values joined into the search haystack.
38 | Catalogue | Medium | A spec facet titled 'Category' (Cat6A / OM4) sat below the main product 'Category' facet — two filters with one name. | Fixed — V2.2 | Displayed as 'Cable category' / فئة الكابل via the localized facet-title map (data key unchanged).
39 | Catalogue | Low | 'IP rating' exists on 8 products but was not offered as a facet. | Fixed — V2.2 | Added to SPEC_FACETS with localized title.
40 | Catalogue | Medium | No noscript fallback — with JS off the catalogue was an empty page with no explanation. | Fixed — V2.2 | noscript note pointing at sales@datacore.com.sa.
41 | Bilingual & RTL | High | Arabic stats band misaligned: figures hugged the left edge of each cell while their labels and marker bars sat right (direction:ltr + text-align:start). | Fixed — V2.2 | html[dir=rtl] .stat b{text-align:end} — figures, bars and labels align together; verified visually.
42 | Bilingual & RTL | Medium | Spec facet titles rendered raw English (Resolution, Type, Rack...) on the Arabic catalogue. | Fixed — V2.2 | facet_titles map per language; values stay Latin technical data with dir handling.
43 | Bilingual & RTL | Medium | aria-labels 'Sort', 'Grid', 'List', 'Close', 'Qty' were English on Arabic pages. | Fixed — V2.2 | All localized via PROD_STR.
44 | Bilingual & RTL | Low | Social icon labels read 'Datacore on LinkedIn' (English) on Arabic pages. | Fixed — V2.2 | Labels are the network name alone — language-neutral.
45 | Bilingual & RTL | Low | Products page breadcrumb lacked the aria-label the other pages' breadcrumbs have. | Fixed — V2.2 | Localized 'Breadcrumb' label added.
46 | Bilingual & RTL | Medium | Arabic grammar slip in the partners heading: الشركات المصنعة المعتمدون — mixed agreement (non-human plural takes feminine singular). | Fixed — V2.2 | Now الشركات المصنّعة المعتمدة لتركيب أنظمتها.
47 | Bilingual & RTL | Medium | Arabic pages never loaded IBM Plex Mono although the catalogue hardcodes it for SKUs/part numbers — they fell to a generic monospace, losing the 0/O-distinction rationale. | Fixed — V2.4 | Plex Mono added to the AR font query, replacing two Archivo weights that Plex Sans Arabic shadowed entirely (net bytes ~neutral).
48 | Bilingual & RTL | Low | Navigation says مقالات تقنية while the page itself is titled ملاحظات تقنية — inconsistent naming for the same section. | Open — minor | Left for the native Arabic review to settle one term; flagged in the review notes.
49 | Bilingual & RTL | Critical | The Arabic copy is a first draft awaiting native technical review — sector vocabulary (التيار الخفيف، النداء والإخلاء الصوتي، discipline names) must match the client's tender language. | Blocker — client input | Unchanged by design; existing launch blocker. Do not ship AR without this pass.
50 | Bilingual & RTL | High | hreflang alternates used relative URLs (invalid per Google's spec) and there was no x-default. | Fixed — V2.2 | Absolute URLs on the production origin plus x-default pointing at the English page.
51 | SEO & metadata | High | No canonical URLs on any page. | Fixed — V2.2 | rel=canonical to the production origin on all 20 pages.
52 | SEO & metadata | High | No Open Graph or Twitter metadata — links shared to WhatsApp/LinkedIn (the client's primary channels) rendered as bare URLs. | Fixed — V2.2 | og:type/site_name/title/description/url/locale + twitter:card on every page.
53 | SEO & metadata | Medium | No favicon — a 404 on /favicon.ico and a generic tab icon. | Fixed — V2.2 | SVG favicon built at build time from the actual logo mark, inlined as a data URI.
54 | SEO & metadata | Low | No theme-color or color-scheme declarations. | Fixed — V2.2 | theme-color = accent teal; color-scheme:light in the stylesheet.
55 | SEO & metadata | Medium | No robots.txt. | Fixed — V2.2 | Generated by build.py, pointing at the sitemap.
56 | SEO & metadata | Medium | No sitemap.xml. | Fixed — V2.2 | Generated with the 14 indexable pages and lastmod dates.
57 | SEO & metadata | Medium | No structured data anywhere. | Fixed — V2.2 | Organization JSON-LD (facts strictly from content.py) on home + contact. LocalBusiness per office, BreadcrumbList, Service/Product/Article remain recommended with the new templates.
58 | SEO & metadata | Low | Utility pages (terms/privacy stubs, 404) must not be indexed while placeholder. | Fixed — V2.2 | meta robots noindex baked into those templates.
59 | SEO & metadata | Low | Two of the three insight posts share the same date (3 March 2026). | Open — minor | Editorial: confirm intended publish dates with the client before launch.
60 | SEO & metadata | Medium | Posts lack machine-readable dates (time/datetime) and Article schema. | Recommended next | Build with the blog-post template (backlog).
61 | Performance & delivery | Medium | The full stylesheet is inlined into every page (~25KB x 20 pages) — right for a file:// prototype, wrong for production caching. | Recommended next | Extract to one cached site.css at deployment; backlog item retained.
62 | Performance & delivery | Medium | The logo SVG is inlined twice per page (~42KB per page). | Recommended next | Serve as cached external assets (dark + light variants) at deployment.
63 | Performance & delivery | High | Google Fonts load pre-consent — the visitor's IP reaches Google before any choice, inconsistent with the map facade's privacy rationale and the site's PDPL posture. | Recommended next | Self-host the three families at launch (font files on the site's own origin); removes the last pre-consent third-party call.
64 | Performance & delivery | Low | Arabic pages loaded two Archivo weights that the Arabic font stack never used — wasted transfer. | Fixed — V2.4 | Dropped in favour of Plex Mono (which is actually used).
65 | Performance & delivery | High | 37 SKUs inlined into products.html is fine; 1,000+ will not be — the page would exceed several MB. | Recommended next | Existing plan holds: server-side products API + pagination before bulk import; catalogue JS already isolates the data source.
66 | Performance & delivery | Low | backdrop-filter blur on the sticky header and chip bar can cost scroll performance on low-end devices. | Open — minor | Acceptable now; replace with a solid background if field testing shows jank.
67 | Performance & delivery | Low | Global smooth scrolling was not disabled for reduced-motion users. | Fixed — V2.4 | scroll-behavior:auto under prefers-reduced-motion.
68 | Performance & delivery | Low | No caching guidance for deployment (HTML vs. hashed static assets). | Recommended next | Document alongside the site.css/logo extraction at launch.
69 | Accessibility | Critical | Reduced-motion users saw an EMPTY hero stack: items rest at opacity:0 and the reveal animation was globally disabled, so the nine-discipline panel never appeared. | Fixed — V2.1 | Under prefers-reduced-motion the stack renders fully visible with no animation.
70 | Accessibility | Medium | Toast notifications ('added to your request') were never announced to screen readers. | Fixed — V2.2 | role='status' live region.
71 | Accessibility | Low | The result count did not announce filter changes. | Fixed — V2.2 | aria-live='polite' on the count.
72 | Accessibility | Low | The mobile Filters toggle had no aria-expanded/aria-controls. | Fixed — V2.2 | Both added and kept in sync.
73 | Accessibility | Medium | The burger button lacked aria-controls, and the menu closed neither on Escape nor after choosing a link. | Fixed — V2.2 | aria-controls; Escape closes; tapping a link closes.
74 | Accessibility | Medium | Opening the mobile menu then widening the window left broken menu styling on desktop (inline styles never cleared). | Fixed — V2.2 | Class-based menu + matchMedia listener resets state at the breakpoint.
75 | Accessibility | Medium | Anchor jumps (footer/services links) buried section headings under the sticky header and chip bar. | Fixed — V2.2 | scroll-margin-top on jump targets clears both bars.
76 | Accessibility | Low | The facet '+N more' expander had no aria-expanded state. | Fixed — V2.4 | aria-expanded added.
77 | Design | High | Partially-filled card grid rows showed large grey 'hole' cells (GRMS row, Background music, Interactive walls, Master clock...) that read as broken placeholders — visible on every visit to Services. | Fixed — V2.2 | Grids rebuilt with per-cell borders instead of the 1px-gap-over-dark trick; partial rows now end cleanly in white. Applied to disciplines, services, values and partners grids.
78 | Design | Medium | Partners grid collapsed 7 -> 2 columns at 1080px (a 7-row tower of names on tablets) and 1 column x 14 rows on phones. | Fixed — V2.2 | 4 columns on tablet, 2 on phones — always full rows.
79 | Design | Medium | Mobile menu was unpolished: no shadow or dividers, the burger icon never became a close icon, and the primary CTA vanished on mobile entirely. | Fixed — V2.2 | Slide-down panel with dividers and shadow, burger swaps to X, full-width 'Request a consultation' inside the menu.
80 | Design | High | The contact map only ever showed Riyadh — the Dubai and Kozhikode offices had no map view at all. | Fixed — V2.2 | Riyadh/Dubai/Kozhikode switcher above the map; before consent it retargets the facade, after consent it swaps the embed. Caption and Directions follow.
81 | Design | Low | Footer blurb was inline-styled with raw hex values, off the token system. | Fixed — V2.2 | .ftr-blurb class in the stylesheet.
82 | Design | Low | Services chips gave no feedback about which discipline was active. | Fixed — V2.2 | Active state follows clicks.
83 | Design | Medium | No print stylesheet — procurement people print pages; chrome, map and drawers printed along with content. | Fixed — V2.2 | @media print hides navigation/footer/map/drawers, flattens colors for paper.
84 | Design | Medium | Glyph icons at 46px float sparsely in 132px thumbnail cells — placeholder look until real photos. | Fixed — V2.3 / client photos | Photo pipeline shipped: drop assets/products/<sku>.jpg and cards, rows and drawer show the photo (icon remains the fallback). Real photography is on the client list.
85 | Design | Low | The company story cites opening Riyadh in 2010; the timeline jumps 2007 -> 2013 and omits it. | Open — minor | Editorial choice — add a 2010 milestone if the client wants the timeline complete.
86 | Design | Low | The insights page is three cards and a CTA — thin as a destination page until real articles exist. | Open — minor | Grows with the blog-post template; the three planned notes are real topics from the old site.
87 | Design | Medium | The CTA band's second button was the dead PDF; the slot now points at the catalogue. | Fixed — V2.2 | Revisit when the company-profile PDF arrives (TODO in build.py).
88 | Design | Low | List view rows get tight on narrow phones (thumb + text + add button in one row). | Open — minor | Grid view is the default and works well on mobile; acceptable.
89 | Content — client input | Blocker | CR and VAT numbers in the footer are dummy digits — legally required for a Saudi commercial site. | Blocker — client input | content.py f_legal, both languages; deliberately obvious dummies until real numbers arrive.
90 | Content — client input | Blocker | Client consent to name Arab Open University, Prince Sattam bin Abdulaziz University and TAQEEM — and to publish project photos. | Blocker — client input | Confirm each before launch.
91 | Content — client input | Blocker | 'Authorised to install' is a strong claim — confirm authorisation is current for all 14 manufacturers, or soften. | Blocker — client input | One list in content.py PARTNERS.
92 | Content — client input | Blocker | Dubai and Kozhikode map pins resolve by address query and are unverified. (Riyadh's coordinates verified: the embed resolves to the Dabbab St / Al Murabba area.) | Blocker — client input | Send coordinates for both; one-line change in OFFICE_GEO.
93 | Content — client input | High | No real installation photography (stock is banned by design) — the projects page carries the biggest upside from real photos of the four named projects. | Blocker — client input | Photo pipeline is ready for products; project photography still needed.
94 | Content — client input | Medium | Standards references (EN 54-16, EN 54-24, ISO/IEC 11801, TIA-568) describe disciplines, not held certifications — confirm wording matches the compliance position. | Blocker — client input | Review the standards strings in content.py disc entries.
95 | Missing for launch | Critical | The 38 service detail pages do not exist — the site's largest SEO and tender-discovery surface. | Recommended next | Highest-value next build. Copy should come from the RESEARCH-PROMPT browsing session output; slugs already mapped in content.SERVICE_SLUGS.
96 | Missing for launch | High | The RFQ back end does not exist — POST /api/rfq receives nothing; submissions live as email/demo payload only. | Recommended next | Payload schema is documented and stable; backlog defines tables, importer, admin.
97 | Missing for launch | High | Excel bulk import for 1,000+ SKUs is not built (manage.py covers day-to-day changes only). | Recommended next | Template data/datacore-product-import-template.xlsx defines the schema; import with staging + per-row validation per backlog.
98 | Missing for launch | Medium | Project detail, blog post and careers templates are missing. | Recommended next | Backlog order: service detail, project detail, blog, careers.
99 | Missing for launch | Medium | No analytics baseline — without four weeks of before-data, the rebuild's effect cannot be demonstrated. | Recommended next | Consent-gated analytics only (site rule: nothing third-party pre-consent).
100 | Missing for launch | Medium | Zero-result catalogue searches are not logged — that list is the client's stocking gap. | Recommended next | Needs the back end; capture from day one.

## Summary
Datacore website V2 — problem register
100 problems identified in the V2.0 baseline (files/datacore-web-repo.zip), audited and worked 2 September 2026.
Version lineage: V2.0 baseline -> V2.1 build fixes -> V2.2 links/a11y/i18n/SEO/design -> V2.3 catalogue manager + photos -> V2.4 polish. Each version is a git commit and a zip in backups/.
Status | Count | Meaning
Fixed in this overhaul (V2.1–V2.4) |  | Verified by check.py (20 pages: structure, links, lang/dir, JS syntax, RTL, contrast) and in-browser testing, EN + AR, desktop + mobile.
Blocker — client input |  | Facts only the client can supply: CR/VAT, Arabic review, consents, manufacturer list, map pins, photography, WhatsApp number, standards wording.
Recommended next |  | Build work with a clear plan already on the backlog: 38 service pages, RFQ back end, bulk import, asset extraction, self-hosted fonts, analytics.
Open — minor |  | Small items deliberately left: editorial choices and acceptable trade-offs, documented so they are decisions rather than accidents.
Total
By severity
Critical
High
Medium
Low
Blocker
Legend: the Register sheet is filterable (row 1). Status colours — green fixed, amber needs the client, blue recommended build work, grey minor/open.